## Sheet1
S.NO | TASKS | DEADLINE | Status | Pre-Requists
1 | Marketplace flow development completion Part-1 | 2026-06-12 | Pending
2 | Marketplace flow development completion Part-2 | 2026-06-15 | Pending
3 | Comparison with Deel and Fiverr (etc) and Corrections | 2026-06-16 | Pending
4 | UI Checking and Improvement | 2026-06-17 | Pending
4 | Integrations | 2026-06-18 | Pending
5 | Alpha Testing | 2026-06-19 | Pending
6 | Beta Testing | 2026-06-20 | Pending